ExAOC Interim Milestones – 10/12/04

| Effort (team) | MS 1 | MS 2 | MS 3 | MS 4 | WBS MS |
| --- | --- | --- | --- | --- | --- |
| system requirements, error budget (Macintosh) | initial error budget & preliminary subsystem goals – 7/16/04 done | final error budget & subsystem goals – 9/20/04 90% , pending mid-term review | system performance verified with simulations – 12/13/04 | final system performance section of CoD – 1/10/05 | prelim. budget inputs – 9/10/04 |
| science case (UCB, et. al.) | completed science-drivers matrix and support – 7/23/04 done | draft Initial OCDD – 10/18/04 done, pending mid-term review | Initial OCDD – 12/13/04 | final science case section of CoD – 1/10/05 | prelim. budget inputs – 9/10/04 |
| system engineering (HIA) | preliminary subsystem interfaces – 8/26/04 done | draft Initial FPRD – 10/18/04 90%, pending mid-term review | Initial FPRD – 12/13/04 | final documentation package – 1/28/05 | prelim. budget inputs – 9/10/04 |
| adaptive optics (LLNL) | preliminary optical requirements and specifications - 7/30/04 done | final subsystem requirements, optical conceptual design (including WFS) – 10/18/04 done (except WFS) , pending mid-term review strawman AO computer design – 10/18/04 done, pending mid-term review | finalized algorithms and AO computer conceptual design, final DM selections, and final CCD selection – 12/28/04 | final AO conceptual design – 1/10/05 | prelim. budget inputs – 9/10/04 |
| coronagraph (AMNH) | preliminary optical requirements and specifications - 7/30/04 done | science instrument interface definitions – 8/30/04 done | fully fleshed-out coronagraph optical design – 10/18/04 very preliminary design complete (slightly behind due to shift in responsibility for the design (will be able to recover)) completed simulations and manufacturability analysis – 12/15/04 | final coronagraph conceptual design – 1/10/05 | prelim. budget inputs – 9/10/04 |
| calibration (JPL) | strawman calibration approach (hybrid & dithering) and specifications – 7/30/04 done | final calibration specifications and interface definition – 10/18/04 specs done, pending mid-term review; report to be written | simulations demonstrating contrast performance with coronagraph and science instrument – 12/15/04 | final calibration conceptual design – 1/10/05 | prelim. budget inputs – 9/10/04 |
| IFU (UCLA) | preliminary optical requirements and specifications – 7/30/04 done | preliminary performance modeling, coronagraph interface definition – 8/30/04 done | fully fleshed-out instrument design – 10/18/04 2-weeks behind (will be able to recover when OSIRIS ships) | completed performance modeling –12/15/04 final science instrument conceptual design – 1/10/05 | prelim. budget inputs – 9/10/04 |
| MWI (UdeM) | preliminary optical requirements and specifications – 7/30/04 done | preliminary performance modeling, coronagraph interface definition – 8/30/04 done | fully fleshed-out instrument design – 10/18/04 done, pending mid-term review |  | prelim. budget inputs – 9/10/04 |
| opto-mechanical (UCO/Lick) | flexure analysis of Keck WFS design – 7/30/04 done | preliminary opto-mechanical design (for AO and coronagraph) and specifications – 10/18/04 2-weeks behind (will be able to recover as optical details are firmed up) | preliminary opto-mechanical design (for WFS) and specifications – 11/25/04 | final opto-mechanical conceptual design – 1/10/05 | prelim. budget inputs – 9/10/04 |
| upper/mid-level SW (UCO/Lick, HIA) | preliminary software requirements, system data flows, and telescope interface – 9/30/04 done | preliminary Supervisory / Component Controller Computer (SCC) conceptual design – 10/18/04 done , pending mid-term review | HW/SW subsystem interfaces and Engineering User Interface conceptual design – 11/30/04 | final upper/mid-level SW conceptual design – 1/10/05 | prelim. budget inputs – 9/10/04 |
| management (LLNL) | track project, monthly reports, etc. |  |  | final WBS, schedule, budget – 1/28/05 | prelim. budget – 9/17/04 |